## Production Gate
GAME DEVELOPMENT — PRE-PRODUCTION GATE CHECKLIST
Gate definition: "We know what we are making and we have an idea of how long it will take." Each item must be Approved, Failed, or Deferred before production is declared open.
Gate Review Date: |  |  |  |  | Attendees:
# | Section | Gate Item | What It Means / Evidence Required | Decision | Owner | Notes & Decisions
PRODUCT DEFINITION
1 | Product Definition | Game concept is locked | The core experience is articulated, agreed by the full team, and no longer evolving. Everyone can describe what ECHOSCAPE is in one sentence.
2 | Product Definition | Unique differentiators are defined | The features that make this product distinct from competitors are documented and confirmed as buildable within the current team and budget.
3 | Product Definition | Game Vision is documented | A written Game Vision document exists that clearly positions ECHOSCAPE as a game — not a meditation app. It articulates the player experience, what makes it engaging to play, how game mechanics deliver calm, and why someone would choose it over Calm or Headspace.
4 | Product Definition | Competitive analysis is documented | A written competitive landscape exists covering direct Steam competitors (PLAYNE, SoundSelf, etc.), adjacent wellness apps (Calm, Headspace, TRIPP), and ECHOSCAPE's key differentiators against each. The team can articulate the gap in the market ECHOSCAPE fills.
5 | Product Definition | Early Access feature scope is locked | A written, signed-off list exists of what is IN and what is OUT for the EA release. This includes decisions on all feature areas and scope. Of course, this also includes the decision if we are doing an official EA.
8 | Product Definition | Platform scope is confirmed | Steam Early Access is the primary target. iOS/Android are explicitly post-EA. The team is not carrying mobile scope into the EA build.
9 | Product Definition | Definition of Done exists | Clear acceptance criteria documented for what 'done' means for a soundscape, a UI screen, and the EA build as a whole.
TEAM & RESOURCES
10 | Team & Resources | Engineer is committed for EA window | Current engineer has confirmed in writing their availability and hours-per-week commitment through the full EA development period.
11 | Team & Resources | UI/UX Designer is hired | A designer is identified, agreements signed, and available to start. This is the single hardest critical path dependency.
12 | Team & Resources | Roles and responsibilities are clear | Each team member knows their primary function. Overlap areas are resolved, not assumed.
13 | Team & Resources | Collaboration tools are set up | Version control, project tracking, and async communication tools are live and all team members are onboarded before Sprint 1 ends.
14 | Team & Resources | Hours per week are committed | Each person has committed to a specific weekly hour count. The schedule's 50% velocity assumption is validated against actual availability.
15 | Team & Resources | Applicable agreements are signed and/or in place | If applicable, written agreements covering scope, rate, IP ownership, and termination exist for all contractors before production work begins. NDA's are also in place and ready to be distributed when needed.
SCHEDULE & PLAN
16 | Schedule & Plan | Master dev schedule is accepted | The development schedule has been reviewed by all team members and is accepted as the working plan — not just a document someone made.
17 | Schedule & Plan | WBS and scope is documented | A Work Breakdown Structure exists decomposing the EA release into workstreams, deliverables, and tasks. Scope is bounded: what is in, what is out, and what happens if scope changes.
18 | Schedule & Plan | Sprint cadence is agreed | 2-week sprints with a defined review meeting. First sprint start date confirmed. Everyone knows what happens at sprint review.
19 | Schedule & Plan | Milestones are agreed and dated | All key milestones are reviewed, target dates accepted, and owners confirmed. EA launch date is committed, not aspirational.
22 | Schedule & Plan | Buffer and slip plan is understood | The team knows the buffer sprint exists and what it's for. If EA slips past target, the agreed fallback date is documented.
23 | Schedule & Plan | First-pass KPIs and analytics plan | The team has identified the key metrics to track at and after EA launch (e.g. session length, D1/D7/D30 retention, review score, wishlist conversion, daily active users). A first-pass analytics plan exists — what gets instrumented, how, and how data will be reviewed.
BUSINESS & LEGAL
24 | Business & Legal | Legal entity is formed | The business (LLC or equivalent) is legally established. Required before signing contracts or receiving investment.
25 | Business & Legal | Funding status is clear | Either seed funding is secured, or the team has agreed on a bootstrap plan and knows the minimum viable budget to reach EA.
26 | Business & Legal | Budget model is accepted | The working budget has been reviewed and accepted. Assumptions reflect reality — not placeholders — before money is committed.
27 | Business & Legal | Steam developer account is active | Steamworks fee paid, developer account created, app entry started. Required before any builds can be submitted to Steam.
28 | Business & Legal | IP ownership is clear | All prototype assets (code, audio, art) are owned by the LLC or properly licensed. No orphaned IP from prior contributors.
RISK
29 | Risk | Risk register is populated | The risk register is live with at least the top 5 project risks, each with an owner, mitigation plan, and contingency.
APPROVED |  | 0 | FAILED |  | 0 | 0
← Approved count |  |  | ← Failed count |  |  | ← Deferred count

## How to Use
HOW TO USE THIS CHECKLIST
WHEN TO USE | Run as a structured gate review meeting before declaring the project in production. Recommended: Founder, PM, Engineer at minimum.
GATE DEFINITION | "We know what we are making and we have an idea of how long it will take." Every item tests one of those two criteria.
APPROVED | Item is complete, documented, and agreed. Evidence exists.
FAILED | Item is not met and cannot be met before production begins. Production should not start.
DEFERRED | Not met but team agrees it is acceptable to proceed — with a specific resolution date recorded in Notes.
NOTES COLUMN | Capture the rationale for every decision, especially Deferred items. Record who made the call and when.
FAILED ITEMS | Any Failed item is a blocker. Production should not open until all Failed items are resolved or changed to Deferred with team agreement.
SUMMARY ROW | Tallies Approved, Failed, and Deferred counts automatically. Goal: all 31 items Approved or Deferred, zero Failed.