## Dev Schedule
ECHOSCAPE — STEAM DEVELOPMENT SCHEDULE ¦ Launch Target: December 2026
Part-time team · 2-week sprints · May 4 – Dec 2026 · Assumptions: 5 soundscapes at launch, controller + kb/mouse, designer hire Sprint 2
Phase | Workstream | Task | Owner | Status | Priority | Notes | S1 May 04 | S2 May 18 | S3 Jun 01 | S4 Jun 15 | S5 Jun 29 | S6 Jul 13 | S7 Jul 27 | S8 Aug 10 | S9 Aug 24 | S10 Sep 07 | S11 Sep 21 | S12 Oct 05 | S13 Oct 19 | S14 Nov 02
PRE-PRODUCTION
Pre-Production | Production | Project kickoff — goals, tools, meetings, Jira/Trello setup, workspace established | PM | In Progress | High |  | █
Pre-Production | Production | Define project vision | Founder | In Progress | High
Pre-Production | Production | Define project KPI's | Founder | In Progress | High | Might start with just Early Access KPI's?
Pre-Production | Production | Define product scope: Launch, MVP, Early Access/Friends & Family | Founder | In Progress | High |  | █
Pre-Production | Production | Define Gates: Pre-Pro, Alpha, Beta, Launch | PM | Not Started | High | Dependent on project scope and KPI's
Pre-Production | Production | Break Scope into WBS (and update this schedule) | PM | Not Started | High
Pre-Production | Production | Finalize team — confirm engineer, begin designer search | PM | Not Started | High | Related to WBS & Scope | █
Pre-Production | Engineering | Prototype audit — document current state in Unreal | Engineer | Not Started | High | Identify gaps vs. EA feature list | █
Pre-Production | Engineering | Establish version control (Git / Perforce) & CI pipeline | Engineer | Not Started | High |  | █
Pre-Production | Production | Create master dev schedule (this doc) + sprint cadence | PM | In Progress | High |  | █ | █
Pre-Production | Design | Designer onboarding — brief, style guide review, asset audit | Designer | Not Started | Medium | Assumes hire by Sprint 2 |  | █
Pre-Production | Design | Define UI/UX structure: menus, settings, session screens | Designer (Founder?) | Not Started | High | Wire-frames only at this stage |  | █
Pre-Production | Engineering | Technical spike: haptic controller input in Unreal | Engineer | Not Started | Medium | Validate feasibility before committing to scope (haptics might already be funtional) |  | █
Pre-Production | Production | Steam developer account confirmed | Founder | Not Started | Low | $100 Steam fee (Could be pushed) |  | █
Pre-Production | Production | Pre-Production Gate | All | Not Started | High | Are we really ready for production?
◆ M2 — Haptic tech spike complete | [7 empty] | ◆
CORE DEV
Production | Engineering | Haptic feedback system — base implementation | Engineer | Not Started |  | Depends on tech spike result |  |  | █
Production | Founder | Learn SFX archtecture in UE5 | Founder | Not Started
Production | Design | UI wireframes → hi-fi mockups: Main menu + soundscape select | Designer | Not Started |  |  |  |  | █ | █
Production | Engineering | Soundscape framework refactor — support 5 environments | Engineer | Not Started |  | Current proto has 2-3; expand to 5 |  |  | █ | █
Production | Founder | Create new Sound Scapes | Founder | Not Started |  | Create as many as possible - get some ready for post-launch release/purchases
Production | Engineering | Session tracking system (duration, streak, history) | Engineer | Not Started |  | Data stored locally first; cloud save in Beta |  |  |  | █ | █
Production | Design | UI implementation: Main menu in Unreal | Designer | Not Started |  | Engineer support needed for widget binding |  |  |  | █ | █
Production | Engineering | Soundscape #3 — audio integration | Engineer | Not Started |  | Not sure how many soundscapes are available, and can't imagine it would take 2 months to implement one |  |  |  |  | █ | █
Production | Design | UI implementation: In-session HUD + controls overlay | Designer | Not Started | [6 empty] | █ | █
Production | Engineering | Haptic feedback — per-soundscape tuning (Env 1-3) | Engineer | Not Started | [6 empty] | █ | █
Production | Engineering | Soundscape #4 — audio integration | Engineer | Not Started |  | Not sure how many soundscapes are available, and can't imagine it would take 2 months to implement one | [5 empty] | █ | █
Production | Design | UI implementation: Settings screen (audio, haptic, display) | Designer | Not Started | [7 empty] | █ | █
Production | Engineering | Soundscape #5 — audio integration | Engineer | Not Started |  | Not sure how many soundscapes are available, and can't imagine it would take 2 months to implement one | [6 empty] | █ | █
Production | Engineering | Haptic feedback — per-soundscape tuning (Env 4-5) | Engineer | Not Started | [8 empty] | █ | █
Production | Design | UI implementation: Progression / session history screen | Designer | Not Started | [8 empty] | █ | █
Production | Engineering | Controller + keyboard/mouse input polish pass | Engineer | Not Started |  | Both input methods fully functional (assuming Mike wants KB&M) | [7 empty] | █
Production | Production | Mid-point dev Gate | All | Not Started |  | Gate: decide if scope needs trimming, are we on track? Do we need to adjust the plan? | [7 empty] | █
◆ M3 — All 5 soundscapes playable (rough) | [10 empty] | ◆
◆ M4 — Full UI integrated, mid-point review | [13 empty] | ◆
ALPHA
Alpha | Engineering | Steam SDK integration — Steamworks API setup | Engineer | Not Started | [10 empty] | █
Alpha | Engineering | Steam achievements — implement 5-8 achievements | Engineer | Not Started | [10 empty] | █
Alpha | Engineering | Steam Cloud Save — session data sync | Engineer | Not Started | [10 empty] | █ | █
Alpha | Design | Art & UI pass — visual consistency across all 5 environments | Designer | Not Started | [10 empty] | █ | █
Alpha | Engineering | Internal alpha build — full playthrough QA | Engineer | Not Started | [11 empty] | █
Alpha | Production | Alpha test with 5-10 external playtesters | PM | Not Started |  | Use existing prototype tester network | [9 empty] | █
Alpha | Production | Bug triage — prioritise for Beta | PM | Not Started | [11 empty] | █
◆ M5 — Alpha build with Steam SDK | [15 empty] | ◆ |  |  |  |  | Need to define alpha - detailed checklist of requirements.
BETA / POLISH
Beta / Polish | Engineering | Bug fixes — P1 and P2 issues from Alpha | Engineer | Not Started | [12 empty] | █
Beta / Polish | Design | Onboarding / tutorial flow — first-run experience | Designer | Not Started |  | Critical for EA reception | [10 empty] | █
Beta / Polish | Engineering | Performance optimisation — framerate, load times | Engineer | Not Started | [12 empty] | █ | █
Beta / Polish | Design | Steam store page assets — capsule art, screenshots, trailer cuts | Designer | Not Started | [12 empty] | █ | █
Beta / Polish | Engineering | Steam store page — description, tags, pricing set | Engineer | Not Started |  | Coordinate with PM (Greg) on copy | [11 empty] | █
Beta / Polish | Production | Beta test with 15-20 external testers | PM | Not Started |  | Wishlist campaign launches here | [11 empty] | █ |  |  | Need to discuss if we have enough time here to analyze and implement Beta feedback
Beta / Polish | Production | Press kit — screenshots, GIFs, fact sheet | Founder | Not Started | [13 empty] | █
◆ M6 — Beta complete, store page live | [17 empty] | ◆
LAUNCH PREP
Launch Prep | Engineering | Final build — RC1 candidate submitted to Steam | Engineer | Not Started | [14 empty] | █
Launch Prep | Engineering | Steam review process — respond to any Valve feedback | Engineer | Not Started |  | Allow 2-week buffer for resubmission | [12 empty] | █ |  | Not sure if Valve provides feedback.
Launch Prep | Design | Launch day assets — store banners, social graphics | Designer | Not Started | [14 empty] | █
Launch Prep | Production | Influencer + press outreach — review keys distributed | PM | Not Started | [14 empty] | █
Launch Prep | Production | Early Access launch day — Steam go-live | PM | Not Started |  | 🎯 TARGET: December 2026 | [12 empty] | █ |  | Need to define whether EA is needed. Might just go wide if the Beta test goes well
◆ M7 — EA LAUNCH 🎯 | [18 empty] | ◆
BUFFER
Buffer | Production | Slip buffer / post-launch patch sprint | All | Not Started |  | Use if launch slips; otherwise EA post-launch patch | [13 empty] | █

## Sprint Plan
Each sprint = 2 weeks. Part-time team (~50% velocity). Update 'Status' each sprint review.
Sprint | Dates | Phase | Focus / Goal | Key Deliverables | Risks / Flags | Status
Sprint 1 | May 04 – May 17 | Pre-Production | Kickoff, scope lock, tech setup | • Feature scope doc signed off • Repo + Jira live • Engineer confirms haptic feasibility • Steam account active | Designer not yet hired — schedule slips if Sprint 2 onboarding delayed | Not Started
Sprint 2 | May 18 – May 31 | Pre-Production | Designer onboards, haptic spike, UI structure | • Designer hired and briefed • Haptic tech spike complete (go/no-go) • UI wireframes started • Steam app skeleton | Haptic scope risk: if spike fails, haptics defer to post-launch | Not Started
Sprint 3 | Jun 01 – Jun 14 | Production | Haptic base + soundscape framework | • Haptic feedback base layer in Unreal • Soundscape system supports 5 slots • Soundscape #3 environment started |  | Not Started
Sprint 4 | Jun 15 – Jun 28 | Production | Session tracking + menu UI | • Session duration/streak tracking • Main menu UI implemented • Soundscape #3 complete |  | Not Started
Sprint 5 | Jun 29 – Jul 12 | Production | HUD + soundscape #4 | • In-session HUD + controls overlay live • Soundscape #4 complete • Haptic tuning Envs 1–3 | Mid-point: all 5 soundscapes playable (rough) ◆ | Not Started
Sprint 6 | Jul 13 – Jul 26 | Production | Settings + soundscape #5 | • Settings screen (audio, haptic, display) • Soundscape #5 complete |  | Not Started
Sprint 7 | Jul 27 – Aug 09 | Production | Progression screen + haptic polish | • Session history / progression screen • Haptic tuning Envs 4–5 |  | Not Started
Sprint 8 | Aug 10 – Aug 23 | Production | Input polish + mid-point review | • Both input methods (controller + kb/mouse) complete • Mid-point scope review — cut if needed • Full UI integrated ◆ | GATE: If behind, identify scope cuts for Alpha | Not Started
Sprint 9 | Aug 24 – Sep 06 | Alpha | Steam SDK + achievements | • Steamworks SDK integrated • 5–8 achievements implemented • Cloud save in progress | Steam review can take 1–2 weeks — build in buffer | Not Started
Sprint 10 | Sep 07 – Sep 20 | Alpha | Steam cloud save + alpha test | • Steam Cloud Save complete • Internal alpha build (full playthrough) • 5–10 external alpha testers • Bug triage ◆ | Alpha test feedback may require scope adjustment | Not Started
Sprint 11 | Sep 21 – Oct 04 | Beta / Polish | Bug fixes + tutorial flow | • P1/P2 bugs resolved • Onboarding / first-run tutorial • Store page assets in progress | Tutorial is critical — poor onboarding tanks EA reviews | Not Started
Sprint 12 | Oct 05 – Oct 18 | Beta / Polish | Performance + store page live | • Performance pass (fps, load times) • Steam store page complete with assets • 15–20 beta testers • Press kit ready ◆ | Wishlist campaign begins here — start influencer outreach | Not Started
Sprint 13 | Oct 19 – Nov 01 | Launch Prep | RC1 + Steam submission + launch | • Release candidate submitted to Steam • Valve review (allow 5–7 days) • Launch day assets ready • EarlyAccess / F&F GO-LIVE 🎯 ◆ | Allow 2-week buffer if Valve requests changes | Not Started
Sprint 14 | Nov 02 – Nov 15 | Buffer | Slip buffer / Day-1 patch | • Use if Sprint 13 slips • Otherwise: first post-launch update • Community feedback triage | Built-in buffer — do not schedule new features here | Not Started

## Assumptions & Scope
ECHOSCAPE — SCHEDULE ASSUMPTIONS & EA SCOPE
KEY ASSUMPTIONS
Project start | May 4, 2026 | Adjust all sprint dates if changed
Launch target (EA or not?) | December 2026 | Sprint 13 end = Nov 30; Valve review in Dec
Hard deadline? | No — can slip to Spring 2027 | Buffer sprint (S14) provides 2-week slip
Team availability | Part-time / nights & weekends | ~50% of full-time velocity assumed
Sprint velocity | ~50% of FT | Full-time equivalent: this is a ~14-month scope compressed to 7 | Maybe 25% of FT
Engineer status | Current engineer confirmed for now | ⚠ Retention risk — no long-term commitment confirmed | Maybe? Mike to provide an update
Designer status | Not yet hired | ⚠ Critical path item — schedule assumes hire by Sprint 2 (May 18)
Mike (Founder) — role | Soundscape composition & audio content creation | Primary creative output; adds soundscape depth as development progresses | Also - defing and refining vision, MVP, etc
Soundscapes at EA | 5 environments | Prototype has ~2-3; 2 new built during Core Dev
Input support | Controller + keyboard/mouse | Both input methods by Alpha | Does Mike want controller enabled?
Haptics | In scope — pending tech spike | If spike fails in S2, haptics deferred to post-EA update
Steam platform | Steam Early Access launch | Full release ~2 months post-Early Access / Friends & Family | 2 months seems like a good buffer to address EA/F&F feedback
EA FEATURE SCOPE (LOCKED IN SPRINT 1)
✓ Soundscapes | 5 distinct environments | Audio + visual per environment
✓ Sound manipulation | Real-time parameter control | Core prototype mechanic — already exists
✓ Haptic feedback | Per-soundscape haptic tuning | Pending Sprint 2 tech spike
✓ Full UI | Menu, HUD, settings, progression | Currently missing from prototype
✓ Session tracking | Duration, streak, history | Local storage; cloud save in Alpha
✓ Steam integration | Achievements + cloud save | 5–8 achievements at launch | TBD if achievements are part of design
✓ Input methods | Controller + keyboard/mouse | Both tested in Alpha
✓ Onboarding | Tutorial / first-run experience
✗ Mobile / console | OUT OF SCOPE for Steam Launch | Post Steam launch
✗ Subscription / IAP | OUT OF SCOPE for Steam Launch | One-time purchase at launch
✗ Multiplayer | Not a feature | Not in product vision
CRITICAL PATH ITEMS
Designer hire | Must be onboard by Sprint 2 (May 18) | Every week of delay pushes UI delivery by 1 week
Haptic tech spike | Sprint 2 — go/no-go decision | If no-go: haptics deferred, schedule stays intact | Haptics may not be an issue at all
Engineer retention | No long-term commitment confirmed | Have backup contractor identified before Sprint 4
Steam review window | Allow 5–14 days for Valve review | Submit RC1 by Nov 17 at latest for Dec launch | Need to confimr Steam submission timelines
Alpha tester pipeline | Need 5–10 testers by Sprint 10 | Use existing prototype tester network | QA staff is TBD Strive for all internal

## Risk Register
ECHOSCAPE: RISK REGISTER
Risk Likelihood & Severity: 1=Very Low, 2=Low, 3=Medium, 4=High, 5=Very High,
Risk Score (Likelihood x Severity): 1–4=Low ¦ 5–9=Medium ¦ 10–16=High ¦ 17–25=Critical
Risk ID | Date Identified | Date Updated | Risk | Description | Area | Likelihood (1–5) | Severity (1–5) | Risk Score (L×S) | Mitigation Plan | Contingency Date | Contingency Plan | Owner | Notes & Comments
1 | 2026-04-23 |  | No designer on staff | Need to hire a designer | Staffing | 5 | 5 | 25 |  |  |  | Donovan
2 |  |  | Staff working pro-bono | No funding to pay developers |  | 4 | 3 | 12 | Find devs who will work pro-bono, part time | TBD | Equity model? | Wilcox | Some devs might be willing to work in exchange for equity
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0