## Start Here
ECHOSCAPE — MVP / VERTICAL SLICE SCOPE WORKBOOK
WHAT THIS WORKBOOK DOES
This workbook helps you define a single, locked feature scope for the next build of EchoScape, one that serves two jobs at once: an Early Access build users can play, and an investor-ready demo that shows what the finished game will look and feel like.
Because this build needs to satisfy both audiences simultaneously, the quality bar is the higher of the two (investor-ready polish) applied to the narrower of the two scopes (only what's essential). Nothing here is scoped to 'minimum' -- it's scoped to 'essential, but done well.'
HOW TO USE IT
1. Start with the 'Feature Brainstorm' tab. Dump every feature idea you have without judging them (yet).
2. Move to 'MoSCoW Sort'. For each feature, mark it Must / Should / Could / Won't. Use the guidance notes in that tab if you're unsure where something lands.
3. Use 'Value vs Effort' as a gut-check — plot the Must/Should items to see if your instincts about priority match the value-for-effort reality.
4. The 'Open Decisions' tab captures the handful of big questions (soundscape count, visualization approach, rewards system) that need a founder decision before the feature list can be finalized.
5. 'Locked Scope Summary' is the output — the final feature list this whole exercise produces. This becomes the document the team builds against.
A NOTE ON MUST / SHOULD / COULD / WON'T
MUST HAVE — the build does not function or does not represent EchoScape without this. If removed, it's not a smaller EchoScape, it's a different product.
SHOULD HAVE — important to the experience and to investor credibility, but the build still works without it. Cut these second, not first.
COULD HAVE — nice, adds polish, but easily deferred without anyone really missing it in this build.
WON'T HAVE (this build) — explicitly out of scope. Not 'never' — just not now. This list matters as much as the feature list. It protects the timeline from creep.
WHY MVP AND VERTICAL SLICE TOGETHER
Industry practice usually treats these differently: an MVP is built to get feedback from real players, a Vertical Slice is built to prove final quality to investors or leadership. EchoScape is intentionally combining both into a single build. That's a deliberate choice — and it means the team should resist the instinct to cut things 'because it's just an MVP.' Every Must Have item needs to look and feel like the finished game, even if there are fewer of them.

## Feature Brainstorm
FEATURE BRAINSTORM — Dump every idea here first. Don't filter yet.
Category is just for organization. Add as many rows as you need — this list feeds directly into the MoSCoW Sort tab.
Category | Feature / Idea | Description | Source / Notes
Core Loop | Soundscape selection screen | Player chooses which environment/soundscape to enter | Vision Canvas — core loop step 1
Core Loop | Real-time sound manipulation | Controller input directly shapes the soundscape as it plays | Vision Canvas — core loop step 2 (already in prototype)
Core Loop | Responsive environment feedback | Visual/audio environment reacts immediately to player input | Vision Canvas — core loop step 3
Core Loop | Session end / outcome screen | Session closes with some kind of summary (time in flow, calm score) | Vision Canvas — core loop step 5
Visualization | Real-time generative visuals (Jeff Minter / Pixel Junk 4AM style) | Visuals procedurally generated from live audio input — full rendering engineer territory | Alex Sulman notes
Visualization | Pre-baked reactive visuals (UX-faked) | A smaller set of pre-built visual states that crossfade/react to input — no dedicated rendering engineer needed | Alex Sulman notes / your question
Visualization | Simple gradient / particle visualizer | Lightweight ambient visual layer, not fully procedural | Alex Sulman notes — Pixel Junk 4AM 'simple visualizer with gradients'
Onboarding | Guided meditation as tutorial | First-time experience teaches controls inside a calming guided session rather than a menu tutorial | Alex Sulman notes
Onboarding | Premade guided sequence (Guitar Hero-style) | Player follows a sequence with marks to hit, teaches mechanics through gentle guidance | Alex Sulman notes
Engagement | Login day counter (not streaks) | Tracks total days logged in, light-pressure milestone rewards (e.g. every 50 days) | Cole Morgan notes — Warframe reference
Engagement | Playtime milestone rewards | Tracks total minutes/hours used, rewards at milestones | Cole Morgan notes — needs AFK/timeout protection
Engagement | Session-count rewards | Rewards for completing X sessions of Y length (10 min x10, x25, x50...) | Cole Morgan notes
Engagement | Leaderboards | Total time, sessions completed, logins — opt-in due to competitiveness risk | Cole Morgan notes — flagged as optional/risky
Engagement | Player check-in dialogue | Game asks how the player is feeling, suggests soundscape, asks afterward if it helped | Alex Sulman notes — 'dialogue with the player'
Engagement | Difficulty / accuracy modes (Easy/Normal/Hard) | Optional structured challenge layer with accuracy zones for mastery-seeking players | Alex Sulman notes — flagged as possibly contradicting calm goal
Customization | Controller axis-to-modulator mapping | Player can remap which stick/trigger controls which sound parameter | Cole Morgan notes — DualSense example
Customization | Cosmetic / sound effect unlocks | New modulators, sound effects, visual experiences as unlockable content | Cole Morgan notes — flagged as possible monetization vector
Audio Tech | Binaural beat integration | Soundscapes designed around specific binaural frequencies, validated via player feedback | Alex Sulman notes
Social | Friends / referral system | Add friends, refer a friend for rewards | Cole Morgan notes — flagged as lower priority without broader social layer
Social | Player titles / account badges | Status-driven cosmetic rewards visible to others | Cole Morgan notes — needs social features to be valuable
Content | Number of soundscapes/environments | TBD — needs explicit number. Pitch deck mentions '3 environments' free tier reference | Open Decision — see Open Decisions tab
UI | Main menu | Entry point — new session, settings, progression
UI | Settings screen | Audio, controller mapping, accessibility options
UI | Session history / progression screen | Shows past sessions, milestones reached
Platform | Steam build (PC/Mac) | Primary platform for this build | Vision Canvas / Pitch deck
Narrative/Tone | No narrator / no guided voice in core loop | Per Design Pillars — game should not feel like a meditation app with instructions | Vision Canvas — What This Is Not

## MoSCoW Sort
MOSCOW SORT — Sort every feature from the Brainstorm tab
MUST = build breaks without it. SHOULD = important, cut second. COULD = nice, defer easily. WON'T = explicitly out of scope for this build.
MUST | SHOULD | COULD | WON'T | Use the dropdown in column C
Category | Feature | Priority | Rationale | Notes
Core Loop | Soundscape selection screen | MUST | Users need to have a way to customize their experience. Not everyone experiences calm with the same sounds.
Core Loop | Real-time sound manipulation | MUST | This is the core experience
Core Loop | Responsive environment feedback | MUST | This is the core experience
Core Loop | Session end / outcome screen | MUST | Visual feedback and analytics for the user
Visualization | Real-time generative visuals (Jeff Minter / Pixel Junk 4AM style) | COULD | Although ECHOSCAPE is primarily a sound-based experience, there need to be visuals as well. | This is an idea that is being brainstormed, and will likely be developed later on once we have a visual designer
Visualization | Pre-baked reactive visuals (UX-faked) | COULD | (See above)
Visualization | Simple gradient / particle visualizer | SHOULD | (See above)
Onboarding | Guided meditation as tutorial | MUST | This will be used to naturally teach the user the controls. This idea can be expanded upon to created guided meditation "levels"
Onboarding | Premade guided sequence (Guitar Hero-style) | COULD | Guided meditation levels could be worked on for the build after the MVP build is complete
Engagement | Login day counter (not streaks) | MUST | Good analytics for the user to have
Engagement | Playtime milestone rewards | COULD | These can be added for the following build
Engagement | Session-count rewards | COULD | These can be added for the following build
Engagement | Leaderboards | SHOULD | If we can use analytic data for a social "leadboard", that would help drive engagement
Engagement | Player check-in dialogue | COULD | These can be added for the following build
Engagement | Difficulty / accuracy modes (Easy/Normal/Hard) | WON'T | Wait on developing this for the following build
Customization | Controller axis-to-modulator mapping | COULD | This will work with a PS5 controller and phones, but it will not work for the standard gamepad that most people use on Steam (an Xbox controller), as it does not have a gyroscope built-in. | This will be a differentiator for the phone version though, and I believe would be a must for it
Customization | Cosmetic / sound effect unlocks | WON'T | Feature for a future build
Audio Tech | Binaural beat integration | COULD | This would be a plus to have, but could be added later. Not a must have for an MVP
Social | Friends / referral system | COULD | This feature could help drive engagement. It would be a plus to have for the MVP
Social | Player titles / account badges | WON'T | This could wait for a future build
Content | Number of soundscapes/environments | MUST | Need to have enough customization available for the MVP build. Anywhere between 12 to 16 selectable soundscapes would allow for this. Expand on this in future builds.
UI | Main menu | MUST | Need a screen to select the game mode (sandbox or guided session), settings, personal/friend analytics, and a quit game option.
UI | Settings screen | MUST | Yes. Need a screen to at least show the Control layout.
UI | Session history / progression screen | COULD | If this can be done without too much effort for the MVP, it would be a plus to have. If not, wait for a future build.
Platform | Steam or standalone installer build (PC/Mac) | MUST | MVP build will be for computers (PC/Mac). Phone builds will be the followup build. | For the MVP, we want to focus on builiding a standalone installer to send out to users for feedback and analytics.
Narrative/Tone | Narrator / Guided voice in core loop | WON'T | I do not believe we need voiced sessions to start, as this is a self-guided/unguided experience. Potentially could be added down the line though
COUNTS | 10 | 2 | 10 | 4

## Value vs Effort
VALUE vs EFFORT — Gut-check your MUST and SHOULD items
Score Value and Effort 1 (low) to 5 (high) for each feature. Quadrant auto-calculates. Do First = high value/low effort. Avoid = low value/high effort.
Feature | Value (1-5) | Effort (1-5) | Quadrant | Notes
Soundscape selection screen | 5 | 3 | DO FIRST
Real-time sound manipulation | 5 | 4 | DO SECOND
Responsive environment feedback | 5 | 4 | DO SECOND
Session end / outcome screen | 5 | 2 | DO FIRST
Simple gradient / particle visualizer | 3 | 3 | DO FIRST
Guided meditation as tutorial | 5 | 5 | DO SECOND
Login day counter (not streaks) | 4 | 1 | DO FIRST
Leaderboards | 4 | 3 | DO FIRST
Number of soundscapes/environments | 5 | 4 | DO SECOND | 12-16 soundscapes
Main menu | 4 | 1 | DO FIRST
Settings screen | 3 | 1 | DO FIRST
Steam or standalone installer build (PC/Mac) | 5 | 5 | DO SECOND

## Open Decisions
OPEN DECISIONS — The big calls that need to be made before scope can be locked
These are founder-level calls. Each has real cost/scope implications. Fill in the Decision column once made.
# | Question | Why It Matters | Options to Consider | Decision
1 | How many soundscapes/environments ship in this build? | Drives audio production time, environment art time, and how 'complete' the build feels to both players and investors. Too few feels thin; too many delays the build for marginal benefit. | TIA deck references '4 environments' as a free-tier reference point. Consider starting there and confirming it feels substantial enough for an investor and EA demo. | 12-16 soundscapes. You can use 4 at a time. 12 might be the sweet spot between value of customization vs. development time
2 | Real-time generative visuals, pre-baked reactive visuals, or no visualization at all? | This is the single biggest cost/complexity swing in the whole build. True procedural visuals (Jeff Minter / Pixel Junk 4AM style) likely require a dedicated rendering/technical artist. A smaller set of pre-built reactive states can be built by a UX/UI designer with much less specialized cost. | Option A: Full procedural rendering (highest cost, highest wow-factor). Option B: Pre-baked reactive visual states that crossfade (UX-feasible, still feels alive). Option C: Audio-only with minimal/no visual layer (lowest cost, may undersell the experience to investors). | Option B would make the most sense for an MVP. If it makes sense, we can develop upon this in later builds
3 | Are login/playtime/session-count rewards in scope for this build? | Cole's notes offer a credible, low-pressure rewards menu. Alex's notes raise a real philosophical tension: reward loops can work against the calm, intrinsic-motivation goal of the product. This needs a founder call, not just a feature checkbox. | Option A: No reward systems in this build — pure experience, prove the loop first. Option B: Light-touch only (day counter, no streaks, no leaderboards). Option C: Full system (counters + milestones + leaderboards), accepting the tension Alex raised. | Option B. This would give a taste into the rewards system and allow the user to see their analytics
4 | Is a tutorial / onboarding experience in scope, and if so, what form? | Alex's notes are clear that 'sandbox, go have fun' doesn't work for first-time players. But a full guided-meditation-as-tutorial or Guitar-Hero-style guided sequence is real design and engineering work. | Option A: Guided meditation tutorial (matches tone, meaningful build effort). Option B: Lightweight contextual hints only. Option C: No formal tutorial for this build — defer to post-MVP. | Option A, ideally. Option C if this will add too much development time to the MVP build
5 | Is controller customization (axis-to-modulator remapping) in scope? | Cole flagged this as a 'huge plus' but acknowledged it's significant UI/UX and engineering work. For an investor-facing build, a single well-tuned default mapping may demo better than an underbuilt customization screen. | Option A: Fixed, well-tuned default mapping only (lower cost, cleaner demo). Option B: Basic remapping support. Option C: Full DualSense-style customization (defer — likely too much scope for this build). | Option A is perfectly fine for an MVP build. Customization for control mapping can come in a later build
6 | Are difficulty modes / accuracy challenges in scope? | Alex explicitly flagged this as possibly contradicting the calm-focused goal of the product. Needs a clear founder decision rather than letting it drift into the build by default. | Option A: Not in this build — the product is intentionally non-competitive. Option B: A very soft, optional version only. Option C: Include it — calm and mastery aren't mutually exclusive. | Option A. This will increase development time. Once MVP is built, this idea can be expanded upon
7 | Is the player check-in / feedback dialogue in scope? | Alex's idea ('how are you feeling, did this help?') is differentiated and ties directly to the Mount Sinai validation study mentioned in the pitch deck — but it adds UI, copywriting, and potentially data-handling scope. | Option A: Simple pre/post mood check (low scope, ties well to validation study). Option B: Full adaptive dialogue system (higher scope, stronger pitch differentiator). Option C: Defer entirely. | Option A. A quick, easy check-in with how the user is feeling could potentially increase engagement with little development time needed
8 | Steam-only/standalone installer for this build, or does mobile factor in at all? | Vision Canvas and pitch deck both point to Steam-first, but the pitch deck's monetization slide describes a mobile subscription model that wasn't part of earlier monetization decisions. Worth explicitly confirming Steam-only scope for this build. | Confirm: this build is Steam-only. Mobile is a separate, later effort. (Flag: resolve the One-Time Purchase vs Subscription discrepancy between Vision Canvas and Pitch Deck separately.) | For the MVP, we want to focus on builiding a standalone installer to send out to users for feedback and analytics. This build will be sold or monetized.

## Locked Scope Summary
LOCKED SCOPE SUMMARY — The output of this exercise
Once MoSCoW Sort and Open Decisions are complete, copy the final MUST and SHOULD items here. This becomes the document the team builds against.
MUST HAVE (the build does not work without these) |  | Further discussion
Soundscape selection screen |  | Support multiple controller types
Real-time sound manipulation |  | Support keyboard and mouse
Responsive environment feedback | Includes some level of visuals to accompany the audio | Need to determine input scheme for the MVP (touch vs controller)
Session end / outcome screen
Login day counter (not streaks)
Number of soundscapes/environments | Mike would like to shoot for 12 (which is ~4 unique)
Main menu
Settings screen | Need to define specific scope here (e.g. toggle the visual screen, dark mode)
Steam or standalone installer build (PC/Mac)
SHOULD HAVE (important, cut second)
Simple gradient / particle visualizer
Leaderboards | How many sessions, how long the sessions are, etc. Need to define specifics
Guided meditation as tutorial | This is about learning the controls. This is not a voice guided meditation.
EXPLICITLY OUT OF SCOPE (this build)
Difficulty / accuracy modes (Easy/Normal/Hard)
Player titles / account badges
Premade guided sequence (Guitar Hero-style)
Playtime milestone rewards
Session-count rewards
Player check-in dialogue
Controller axis-to-modulator mapping
Binaural beat integration
Friends / referral system
Session history / progression screen